## Short Term
Goal Date | Description | Short Term | Goal Date2 | Date Completed2
| Setup SUMO | - | - | -
|  | Install and run a simple network |  | 2022-11-14
|  | Control Vehicle Speed in Python |  | 2022-11-14
|  | Edit network from within Python |  | 2022-11-15
|  | Create traffic flows |  | 2023-01-11
| Set up a multi-action DQN agent in simple Python Env- runs based on trajectory (action) instead of singular "time" steps | - | - | -
2022-11-18 | Implement a simple DQN in SUMO to drive speed limit | - | - | -
| Create DQN Agent to navigate corridor most fuel efficiently | - | - | -
|  | Get gap and SPaT data |  | 2022-11-25
|  | Fix issue where car learns to wait to increase reward | 2022-11-26 | -
Train with nonvariable light times
2023-01-18 | Add other traffic and retrain
2023-01-20 | Observe Fuel Consumption for entire corridor
Add variable light times as observation
Add more intersections to observation
Write Paper

## Thesis Ideas
Idea | Description
How fuel efficient agent functions in traffic compared to rule based
How multiple agents compare in traffic
Acceleration based vs accel/constant/decel agents compare
How RL vehicle effects fuel consumptions of entire corridor stretch